## Sample
Project Tracker
Company Name: |  |  | Your Company Name Here
| Today's Date: |  | 2021-10-11 | (For the example, the date does not change)
Project Name | Start Date | Projected / Actual Completion | Projected Length (Days) | Actual Progress (Days) | Days to Completion | Contract Amount | Invoice 1 Sent | Progress Payment 1 | Invoice 2 Sent | Progress Payment 2 | Invoice 3 Sent | Progress Payment 3 | Invoice 4 Sent | Progress Payment 4 | Invoice 5 Sent | Progress Payment 5 | Amount Due
Modern Builders Model | 2021-10-01 | 2021-11-01 | 31 | 10 | 21 | 7500 | 2021-10-02 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 | 6500
Jumbo Townhouses | 2021-08-12 | 2021-12-31 | 141 | 60 | 81 | 25000 | 2021-08-13 | 8500 | 2021-09-30 | 5500 | 2021-10-31 | 5500 |  | 0 |  | 0 | 5500
Mega Addition | 2021-11-01 | 2022-01-31 | 91 | -21 | 112 | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15000
Super Custom Home | 2021-07-04 | 2021-10-01 | 89 | 99 | -10 | 45000 | 2021-07-05 | 20000 | 2021-09-25 | 20000 | 2021-10-01 | 5000 |  | 0 |  | 0 | 0
Easy Peezy Lot Releasy | 2021-10-07 | 2021-10-15 | 8 | 4 | 4 | 750 | 2021-10-07 | 750 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Easy Peezy Lot Releasy | 2021-10-07 | 2021-10-15 | 8 | 4 | 4 | 750 | 2021-10-07 | 750 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44480 | -44480 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 93250 | [10 empty] | 27000
Formulas:
Projected Length (Days) = DAYS([Projected / Actual Completion],[Start Date])
Actual Progress (Days) = DAYS(D3,[Start Date])
Days to Completion = DAYS([Projected / Actual Completion],D3)

## Template
Project Tracker
Company Name: |  |  | Your Company Name Here
| Today's Date: |  | 2021-10-10 | (Date changes automatically)
Project Name | Start Date | Projected / Actual Completion | Projected Length (Days) | Actual Progress (Days) | Days to Completion | Contract Amount | Invoice 1 Sent | Progress Payment 1 | Invoice 2 Sent | Progress Payment 2 | Invoice 3 Sent | Progress Payment 3 | Invoice 4 Sent | Progress Payment 4 | Invoice 5 Sent | Progress Payment 5 | Invoice 6 Sent | Progress Payment 6 | Amount Due
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 44479 | -44479 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
[6 empty] | 0 | [12 empty] | 0
Instructions:
1. Add your project name in Column A
2. Add your start date (current or future) in Column B (The cell will change from yellow to white)
3. Add your projected completion date in Column C (The cell will change from yellow to white). Columns D, E, & F, will automaticallly fill.
4. Columns D, E, & F, will automatically fill. When there is ample time to complete the project, based on projections, the cell will change from red to green. When the project is within 10 days of its projected completion date, the cell will change from green to amber. Whent the project goes beyond its completion date the cell turns red again.
5. Enter the contracted amount (or estimated/not to exceed total if time & material) in Column G
6. As invloices are created and sent, enter them in the corresponding columns to the right. The cell will change from yellow to white.
7. As progress payments are received, enter them as well. The balance due will remain in red text, until the balance reaches zero.
8. To add more rows, highlight one row and copy (cntl+C), then highlight the row in which you want to insert the new row above, right click, and choose "insert copied cells."
9. The "Today's Date" cell at the top is formulated to automatically dispay the actual date, each day the spreadsheet is open.
10. Columns N through S have been hidden. They contain additional invoice periods and progress payments. To view them, highlight both columns M & T, right click, and choose "unhide."
Formulas:
Projected Length (Days) = DAYS([Projected / Actual Completion],[Start Date])
Actual Progress (Days) = DAYS(D3,[Start Date])
Days to Completion = DAYS([Projected / Actual Completion],D3)