## Slide 1: Wilderness Navigation Fall 2020

## Slide 2: Contents
Key Points
Timeline
Activity Description
Framework for online Workshop

## Slide 3: Key Points
New stuff
  Briefing
  Online Workshop
  Small Group Field Trips
Guiding Principals
  Keep it simple
  Encourage discussion and interaction
  Ensure course objectives are met

## Slide 4: Timeline
 |  | Note
7/9 – 9/30 | Course Dev | 
7/29 | Go / No Go | 
8/3 | Post Course | 9/1 Close registration
9/1 | Post Course Briefing | New Activity
9/7 – 9/18 | Online Map & Compass | Legacy
9/21 – 10/2 | Online GPS | Legacy
9/26 | FT Instructor Training | Instructors only
TBD | Workshop Instructor Training | 
10/7 & 10/14 | Online Workshop | New Activity
10/10 | FT Instructor Training | w/Student prototype
10/17, 10/24, 10/31 | Field Trips | 

## Slide 5: Posting
Course will be posted on Aug 3rd.
  Registration closes 9/1 (allowing us time to make adjustment due to Covid-19)
Activities to include:
  Intro Briefing
  Online Map and Compass
  Online GPS
  2x Online Workshops
  6x Small Group Field Trips
36 Student Limit

## Slide 6: Briefing
Structure, single 30min live ZOOM, recorded
Purpose, to provide an overview of the the course and build a sense of collaboration
Main points:
  Course structure as a result of Covid-19
  What’s new, what we’re trying to achieve and how important feedback is
  How to ask questions and provide feedback

## Slide 7: Online Map & Compass
Structure:
  Litmos no changes from last year
  Self-paced, 12 days to complete
Instructors:
  1x primary lead activity administration
  1x support answers subject matter questions
Key points
  No student materials required
  All questions must be answered before moving to next topic

## Slide 8: Online GPS
Structure:
  Updated Google Slides hosted on Google Drive
  Seattle manages content and doc protections
  Self-paced, 12 days to complete
Instructors
  1x lead, primarily administration
  1x support, answers subject matter questions
Key points
  Students are required to upload files demonstrating that they have completed activity tasks
  Instructors need to check uploads for competition

## Slide 9: Online Workshop - DRAFT
Structure
  Live ZOOM meeting with Mod B & C breakout rooms
  Two, single evening online workshops. Size TBD
  1x Activity Lead
  1x (?) Instructor for each breakout room
Key Points
  Use existing content wherever possible, not required
  Breakout rooms, small is better
  Leverage online tools and digital docs where ever possible

## Slide 10: Online Workshop - DRAFT
Required development steps
  High-level design
  Walk through, maybe more that one
  Repository for collecting student docs.
  Do we need to offer an in-person mentoring session?
  GPS Module “A” to be moved to Field Trip
  What to do with “Disaster in the Alps”?

## Slide 11: Workshop Organization – DRAFT
Main Room
RM MA #1
RM MA #2
RM WF #1
RM WF#2
1x Inst
St Grp #A
1x Inst
St Grp #B
1x Inst
St Grp #C
1x Inst
St Grp #D
Activity Lead moves students, manages time
Instructor stays in room, ensures subject expertise
Students move as a group between breakout rooms

## Slide 12: Online Workshop Schedule - DRAFT
Welcome (20mins)
  Explain flow of events
  Explain how to use ZOOM, raise hand to speak
  Leader to assign students to room (need finalized roster)
1st Rotation (40mins + 5mins for logistics)
  Overview, (5mins)
  Tabletop problems (35mins)
2nd Rotation (40mins + 5mins for logistics)
  Overview, (5mins)
  Tabletop problems (35mins)
Wrap-up (10mins)
  Discuss Field Trip

## Slide 13: Welcome - DRAFT
Provided by Activity Lead
Explain movement
Map vs. Actual
  Explain how to view pictures while maintaining ZOOM (split screen as an option)
  Explain / demonstrate how a student can show their map to the instructor using iPhone or Android

## Slide 14: Map vs Actual (Mod “B”) - DRAFT
Use existing document and pictures
Lead
  Places students into breakout room via CSV files
Instructor
  Show how to orientate map, measure a bearing, measure distance
  Will require doc camera
Students
  Work independently using Barring Map,
  Upload answers upon session end
    Need a common repository
  Practice showing map or doc. to instructor
    Need written instructions
Notes: Should pictures be provided prior to workshop? Send link via

## Slide 15: Workflow w/ Tools (Mad “C”) - DRAFT
Basically the same as structure as Mod “B”
Reduce the number of questions keeping only those directly related to goals/objectives
This could be more an interactive lecture than just answering the questions.
  We’ll have Caltopo and Gaia at our figure tips
To be updated

## Slide 16: Online Workshop Materials - DRAFT
Student packet
  Sent one week prior
Pictures, student to download
  Links provided via Welcome email
Barring Map
  Students require to purchase, info provided via course welcome email
Compass w/ scales
  Student required to purchase, recommendations provided via course welcome email
Welcome to the Workshop email
  Provided September 1st
Instructor “Doc camera”
  Instructions provided with welcome instructor email
Instructor Packer
  Link provided with instructor email

## Slide 17: Field Trips
Structure
  Independent small groups 6 students + 2 instructors
  Multiple small groups per day, w/20 min. physical separation
  Follow “then current” Covid-19 guidelines
  Each small group to follow FT syllabus as designed
Instructors
  1x primary lead,
    Manage interface btw club, DNR and Seattle Branch
    To be present onsite through out the day
    Manages rosters, awards badges, tracks volunteer hours
  2x instructors per small group,
    instructors may lead multiple small groups scheduled one week apart
    Goal is to pair one seasoned w/ one freshman